Vale of Glamorgan Council

Welsh Language Scheme

Annual Monitoring Report 2012-13

# Introduction

The council’s current Welsh Language Scheme was approved in March 2012 outlining a commitment to provide Welsh language services on a basis of equality with English. We have continued to implement the accompanying action plan and detail is included with commentary on the progress on each area of work. The plan is reviewed regularly; implementation is coordinated by the Equalities team. Actions are incorporated into departmental service plans, which form an integral part of the council’s performance management framework. This ensures that performance is monitored quarterly by the council’s scrutiny committees.

A Welsh language skills audit took place for staff who use computers.  The initial information was collected by means of special software which loads when a user logs on to their PC. The completion of the form was compulsory and has provided details for all staff who use computers. The outstanding information on staff has been collected since. A second audit will take place in June 2013 as part of the drive to improve our data in line with the Equality Act.

Information is also routinely collected in the Oracle computer system of the skills of applicants for posts within the council.

In the meantime the council is continuing to develop the Welsh language skills of its staff. Fourteen members of staff are currently attending Welsh language courses. We have also offered free sessions on a weekly basis for the last year and these have proved popular and successful. Tea/coffee is provided during the lunch hour and learners are able to practise their Welsh in an informal setting. The first hour is for learners and the second hour is for improvers. Eleven members of staff this year have taken advantage of this opportunity. Several staff have used these sessions as a springboard to join formal courses and others have continued to attend to practise their skills.

The Equalities team continues to work closely with the Welsh for Adults team to encourage more staff to join formal courses and a taster day will be held at the end of May to explain the options for the autumn 2013 term.

We have been disappointed by the dissolution of Menter y Fro and have not yet received a clear indication of where the funding has been re-allocated.

However, we have continued to provide a comprehensive sports programme for all ages through the medium of Welsh.  These include football, netball and athletics as well as multisport which is run by the Urdd. A 5x60 officer is based at Ysgol Gufn Bro Morgannwg on a part-time basis and his role is to engage young people in sport and physical activity in extra-curricular time.

This work underpins the council’s strategic priority to promote the development of a bilingual workforce to support children and young people’s opportunities to use the Welsh language.

Guidance on Welsh language training and publications has been streamlined so that officers are aware of their obligations under the Welsh Language Scheme. This has helped managers to target training within their teams and to be aware of where publications should be produced bilingually.

Welsh language pages are available on the council’s internal Staffnet to inform staff of language developments in the workplace. Guidance documents are published on these pages as well as a copy of the council’s scheme, reports and Publication Guide.

The council has adopted a Content Management System (CMS) to update its website (www.valeofglamorgan.gov.uk). This website provides a prominent toggle button on the front page allowing the user to choose between an English or Welsh interface/content. The domain name www.bromorgannwg.gov.uk points users directly to the Welsh language version of the website. The Welsh website is a replica of the English version, and the council is committed to translating it in its entirety down to the first three layers wherever we have stated we will do so. Beyond three levels, translation of pages and documents will be undertaken according to demand, so that the most popular pages are available bilingually. Following consultation with our Welsh speaking residents, the council has committed in its action plan to ensure that the top ten most popular web pages are fully bi-lingual. Every effort will be made to release key information simultaneously in English and in Welsh, although this will not always be possible and there may be a delay.

Our Welsh Web Translator has recently resigned her post, and the recruitment of a replacement has begun. The post has been advertised, and we are awaiting responses from potential candidates. The council’s website is also being re-launched using a new CMS, and their first job will be to ensure that all existing translated pages have transferred successfully.

Significant work has been undertaken to ensure that electoral information and on-line forms are fully bi-lingual. Interaction with Welsh language web users will increase in order to establish their existing and changing needs and to aid with continuous development.

The accuracy of translation of documents into Welsh is given a high priority throughout the council and all documents are directed to the Welsh translator who is based within the Communications team in the Corporate and Customer Services Department.  Approximately 250 documents have been translated so far this year by the council’s Welsh language translator. These include letters, forms, public notices and council publications. The Welsh language and Web translators have been brought together and Welsh translation software has been purchased by the council to increase productivity. We have contributed to the provision of information for a Wales-wide translation service, and await developments from Welsh Government.

The new Welsh Language Standards will inform how the Council collects and produces information in the future and constructive comments have been forwarded to the Welsh Language Commissioner. We have also responded recently to the Education Minister on Welsh Language Communities in Wales.

1. Welsh Language Scheme Compliance

| WLS 62 |  | Publish and promote the Linguistic Skills strategy. | Raise awareness of staff | Completed; the plan has been implemented and promoted. |
| --- | --- | --- | --- | --- |
| WLS 63 |  | Develop and implement a Welsh Language Training and Development Strategy | Tailored training is available and monitored | The strategy has been drafted and will be reviewed as part of the training needs analysis undertaken by the WLGA |
| WLS 64 |  | Promote and publish the Welsh Language Scheme | Staff are aware of their responsibilities | Completed; the WLS is widely used as a basis for responding to requests. Public information not produced bi-lingually is removed from display and complaints are raised the officer responsible. |
| WLS 65 |  | Ensure that linguistic skills information is collected from all staff | Key information is obtained on staff skills | Information is held on a spreadsheet and is being kept up to date. A new audit will take place in June 2013 and data will be entered onto the Oracle system. |
| WLS 66 |  | Ensure that signage and badges are visible in reception areas | Residents will feel welcome to speak in Welsh when visiting Council premises | Completed; signs are prominent in all reception areas and Welsh speakers wear badges. |
| WLS67 |  | Ensure that adequate numbers of Welsh speaking staff are available in the Contact Centre | Welsh language users are able to access information and services in preferred language | Completed; of 36 Customer Service Representatives in the contact centre eight are fluent Welsh speakers. This represents 22% of the team. |
| WLS 68 |  | Arrange for the translation of all on-line forms and information regarding electoral registration | Arrangements for elections are bilingual | Completed. |
| WLS 69 |  | Ensure that staff who speak Welsh have bi-lingual Email footers | Residents are aware of when they can respond in Welsh | This will be implemented by September 2013 and was discussed with Gareth Smith in the January update meeting. |
| WLS 70 |  | Ensure that the top ten web pages accessed by residents are fully bilingual | The most popular parts of the website are available in Welsh | Completed; now standard practice. |
| WLS 71 |  | Ensure that translation of current news, updates and jobs takes priority over other web translations | The most important elements of the website are translated quickly | Completed; now standard practice. |

| WLS 72 |  | Review the Welsh language content of the website | Regular checks will ensure that Welsh is correctly used | Completed; now standard practice. |
| --- | --- | --- | --- | --- |
| WLS 73 |  | Review the job descriptions and person specifications of reception staff and revise for new staff to include Welsh language abilities | Managers are able to provide Welsh language facilities in frontline areas | Completed. |
| WLS 74 |  | Assist elected members to publicise and improve their skills | Residents are aware of which members are Welsh speaking | 4 training sessions for elected members have taken place in April and May 2013. These were with The Independent Group, Corporate Resources (Scrutiny), the Cabinet and Plaid Cymru. |
| WLS 46 |  | Introduce a “jobs fair” with Barry College and Ysgol Bro Morgannwg to encourage work experience and job applicants with Welsh language skills | Staff skills reflect the needs of the service to provide bilingual services | This action has been amended to enable a working relationship between ourselves and the Welsh champion in Barry and Vale College. Plans are under way for students to visit the call centre for a taster session. |
| WLS 75 |  | Prepare guidance for officers who are involved in partnership working | Officers are aware of the Council’s commitment to the Welsh Language | Completed |
| WLS 76 |  | Ensure that the HR Strategy and Workforce Plan reflect the Linguistic Skills Strategy | Mainstream the LSS as part of workforce planning | Completed |
| WLS 77 |  | Review language used in bi-lingual job descriptions to ensure clarity for Welsh speakers | Clear Welsh is used in job descriptions | The Welsh translator will keep a record of any request for job descriptions and will work with the Corporate Equalities Officer |
| WLS 78 |  | Outline the level of Welsh required in specific job roles | Clarity on level of Welsh for each role | The Corporate Equalities Officer checks on any new advertisements. |

| WLS 79 |  | Undertake a new ‘Mae gen ti ddewis’ campaign to encourage more use of the Contact Centre phone line | The availability of the Welsh Language line is publicised and awareness increased resulting in increased use of the service | Unable to obtain funding to date for this project. |
| --- | --- | --- | --- | --- |
| WLS 80 |  | Provide awareness training to key staff on a regular basis as well as informal opportunities to practise their Welsh skills | Staff are aware of Welsh language issues and are able to improve their skills | Informal language sessions have been running for the last year. Awareness sessions are planned for later in 2013. A successful taster session was held during the Six Nations for staff to learn some basic Welsh and the national anthem. |
| WLS 81 |  | Develop a structured working relationship with Menter y Fro in order to help WL development particularly in leisure and in relation to privatisation | Increased support for learners and residents | Menter y Fro has been disbanded. |
| WLS 82 |  | Include WL issues in recruitment and selection training | Awareness among managers regarding the LSS requirements | Dec 2013 |
| WLS 83 |  | Design and circulate a database for use by departments to register individuals and organisations who wish to communicate with the council in Welsh. | The council is aware of those residents who wish to deal with the council in Welsh | Dec 2013 |
| WLS 6 (on-going |  | Undertake an audit of council publications and documents, and promotional materials | Managers are complying with the Welsh Language Scheme | Completed in February 2013 and is an annual event |
| WLS 7 (cf) |  | Contact centre staff establish and communicate the language preference of customers to back office staff | Welsh language customers receive information in their preferred language | Dec 2013 |

| WLS 9 (cf) |  | Undertake an annual audit of new strategic documents to assess achievement of WLS objectives | All strategic documents are translated as appropriate | Underway; to be completed by the end of June 2013. |
| --- | --- | --- | --- | --- |
| WLS 83 |  | Provide information on linguistic skills in the annual monitoring report | Data is provided to WLB on an annual basis | Completed (see below) |
| WLS 84 |  | Monitor Service Plans to ensure that actions in respect of the Vale Equality Scheme and targets are being effectively implemented | Welsh Language actions are monitored as part of Service Plans | June 2014 |
| WLS 85 |  | Review the current format of job advertisements in order to increase the bilingual content | More bilingual content in advertisements | Deferred due to Job Evaluation and Workforce Planning; to be completed in the second half of 2013. |

2. Welsh Language Frontline Services

Children and Young People’s Partnership

Since the development of the first Children and Young People’s Plan in 2008, the Vale of Glamorgan CYP Partnership has forecasted the demand for Welsh medium education and been planning delivery and provision accordingly.  The original CYPP Plan acknowledged the substantial increase in Welsh speakers.  The proportion is higher among children and young people than for adults. This action has progressed well with the development of a Welsh Education Scheme and a school development plan that is responding well to the identified need for projected Welsh Medium Education.

The Council’s Welsh-medium Education Strategic Plan highlights that despite its large and diverse area, Welsh medium education in the Vale is thriving.  The growing demand is highlighted in the recent establishment of two new Welsh medium schools.

The WESP Group has been established with representatives from various council departments, schools and local Welsh language organisations. The group has developed an action plan to address the strategic priorities of education and include those within the CYPP Plan to ‘promote the development of a bilingual workforce’ and ‘to support children and young people’s opportunities to use the Welsh language’. This involves training Welsh speakers in workforce skills shortage areas and raising awareness of children and young people of their right to use the Welsh language when participating in activities, services and provision.

Examples include: a bilingual youth provision developed within the Youth Service on two separate nights; additional support for year 6 pupils in transition to year 7; development of a Welsh language youth forum; funding for the development of sports activities in conjunction with the Urdd; In addition the Youth Service is working in partnership with the Urdd providing Welsh language curriculum activity training for Welsh speakers and non Welsh speakers, including OCN Courses and School Radio Training.

On an individual basis all partnership members continue to ensure that the Welsh language receives recognition within all their plans and developments. The Corporate Equalities Officer, on behalf of the Vale of Glamorgan Council, advises the partnership on Welsh language issues.

Ability to guarantee a Welsh language service at main receptions, contact centres or one-stop shops

The contact centre has a staff of 35.5 Customer Service Representatives, and during the year the number of Welsh speaking staff has increased to 8 front line call handlers, including three reception trained staff. We are able to provide all contact centre services through the medium of Welsh.

We advertise bilingually one telephone number for the public to use to contact the Council, which includes a dedicated Welsh language option, with every caller to the council given the option to have their enquiry handled through the medium of Welsh. 100% of calls received on the Welsh language line have been able to be answered. The line is fully staffed between 8.00 am and 6.00 pm in line with the contact centre opening hours. In addition to telephone calls, the contact centre is able to respond to other contact channels in Welsh including emails and SMS text messages.

During 2012/13 just over 1,300 calls were answered and dealt with through the medium of Welsh. The council is confident that the majority of enquiries can be answered in just one contact, without having to transfer the caller to other departments within the council. To date there has been a very positive response to the Welsh language service from the Welsh speaking public although numbers of calls have reduced in line with the English line as more customers choose to contact us via SMS and Email.

Standards of Service

The council’s complaints procedure was assessed by the Welsh Language Board in January 2009 and found to be fully compliant. Complaints are logged either on the council’s customer relations system or by departments. Any complaints relating to the implementation of the Welsh Language Scheme are recorded and monitored by the Equalities team. A list of complaints is attached along with any remedial action required.

Complaints received in the medium of Welsh are also recorded as part of the customer relations management software within the contact centre to ensure that a response is sent in Welsh.

3. Scheme Management and Administration

Human Resources – Equality and Diversity – Language Ability

The equalities monitoring form includes questions on candidates’ spoken and written Welsh skills as well as their ability to understand and read Welsh. This information is recorded on the Oracle human resources system.

Our linguistic skills audit has indicated that large numbers of staff have some Welsh skills –  in excess of 400 staff have indicated a basic level of Welsh ability and over 100 declared themselves competent or fluent. A significant number also indicated an interest in learning or improving their skills. This has enabled us to target training invitations and to get in touch with bilingual staff when we need them. It also helps team leaders to plan training.

A further audit will take place in June 2013 as part of the exercise to collect information on protected characteristics.

Procurement

The council’s procurement guidance has been reviewed and the legal contractual arrangements improved to ensure robust consideration of the Welsh Language Scheme. Key contracts include a requirement to comply with the Council’s Welsh Language Scheme.

4.  Linguistic Skills - Comparing service needs and capacity

Welsh in the Workplace Training and Language Awareness Training

Informal sessions have been held on a weekly basis for the last year. Taster sessions are run by the Welsh for Adults team in preparation for the Autumn term.

Elected members were offered language awareness sessions either in their own political groups or as part of the scrutiny meeting. Cabinet members were also briefed. Sessions took place during April and May and were well-received.

5.  Mainstreaming

Equality impact assessments covering all equalities strands including the Welsh language are undertaken on major corporate policies, the council’s budget and on some functions. This helps to ensure that Welsh is mainstreamed and monitored equally with the other issues.

The Welsh language action plan is reviewed regularly by the Equalities team alongside the action plans for other equalities strands. This ensures that the issues are at the forefront of day-to-day developments.

Major council strategies were reviewed during 2012 to ensure that a summary is available in Welsh. Public notices and publications are checked on an annual basis by the Communications team.

Equalities issues are mainstreamed through the council’s performance management framework. All departmental service plans contain equalities objectives, with risks, performance measures and actions. Measures are reviewed quarterly by the relevant scrutiny committee; actions are reviewed six-monthly in the same manner.

The Equalities team has developed the ‘Vale Equalities Scheme’ (VES). This was introduced in 2007 and was based on the Welsh Local Government Association’s Equality Standard of which the Vale Council had achieved level 3. The VES was developed to assist in the ‘mainstreaming’ of equalities matters, with managers in all service areas taking responsibility for equalities. In the first year, managers were set a target to achieve level 1 and then further levels each year. The current target is for all relevant service areas to achieve level 4 and many have already done so. Language is a key element of the VES. The scheme is developed, assessed and monitored by the Equalities team.

The council has an internal officer working group (Corporate Equalities Working Group) through which information is cascaded to departments, and issues can be raised and discussed. It also operates a, Equalities Consultative Forum, which is a formal committee of the council and consists of elected members and representatives from support and campaigning groups. Until recently, Menter y Fro was an active member of the group.

6.  Analysis of Performance by priority and target

The council monitors the implementation of the Welsh Language Scheme through the following mechanisms:

- regular monitoring of action plans

- annual improvement planning, including achievement of targets and a summary of achievement of the Welsh Language Scheme;

- an annual report to the Corporate Management Team, the Scrutiny Committee and the Welsh Language Commissioner.

Annual reports are compiled by the Equalities team in consultation with managers and officers involved in implementation of the scheme. Complaints in implementation are collated by the Equalities team and although these are very few it is important to the Council to identify where improvements can be made. The Council conducts periodic opinion surveys and arranges focus groups to consult Welsh speakers on the standard of service that they are receiving in Welsh.

7.  Publishing Information on performance

The Council collects and reports information on all measures that are national statutory measures and sets targets for them. We have also adopted a limited number of local indicators which assists in measuring progress against this scheme. This information is publicly available via the council’s Improvement Plan and service plans, which are published annually and is available on the council’s website www.valeofglamorgan.gov.uk or www.bromorgannwg.gov.uk.

In addition to this, once approved by Corporate Management Team, the council will publish this report on the Equalities section of the council website along with other data on language matters.

| • The level of conformity with Welsh language among third parties operating on behalf of the Council. The Council will undertake an annual sample of contracts with third parties to identify conformity issues with the requirements for the Welsh language as set out in the Council’s procurement guidance. It will be reported as a percentage of those sampled (numerator and denominator will be provided). | The council’s procurement guidance has been reviewed and the legal contractual arrangements improved to ensure robust consideration of the Welsh Language Scheme. A large contract was reviewed in December 2012 relating to the council’s Leisure Services. Compliance with the council’s Welsh Language Scheme was included. |
| --- | --- |
| • Information on current staffing and recruitment to frontline posts. Frontline posts are those in the ‘front office’ of the Council and will be measured on the basis of these positions. Increasingly, this will come to mean the Onevale contact centre. It will be measured as a percentage of those identified in front line posts (numerator and denominator will be provided). | Of 35.5 Customer Service Representatives in the contact centre eight are fluent Welsh speakers. This represents almost 23% of the team. |
| • Number of staff undertaking training and to what level/degree of proficiency. This will be measured based on the number of staff undertaking Welsh language training provided by the Council. This measure will be reported as a number under each of the categories: Entry and Foundation; Intermediate; Advanced; Advanced/Mastering. | There are currently 15 members of staff who have enrolled on Welsh language training. (Sept 2012) 10 Entry and Foundation 2 Intermediate 3 Advanced |
| • Number of staff with Welsh skills in the Council. This indicator was measured via the Linguistic Skills audit in 2012. A further audit will take place in 2014. | 118 members of staff are ‘competent’ or ‘fluent’ and 400 members of staff have some basic skills. A new audit will take place in June 2013 and new figures will be available for the next annual report. |

| • Number of complaints about implementation of the Welsh Language Scheme. This performance indicator will be measured on the basis of the number of those complaints about the content or implementation of the Welsh language scheme, which will be investigated by and responded to by the Equalities Team. | 10 complaints have been received during 2011/12. Detail is recorded by the Corporate Equalities Officer and a summary is attached as Appendix A. |
| --- | --- |

8.  Additional Information

In the next year the council will build on its current successes in Welsh language provision and will develop further awareness sessions as well as working with Barry and the Vale College and the Welsh for Adults team.

Consultation took place with residents as part of the preparation for the Welsh Language Scheme and has been incorporated in the action plan.

Welsh Language Scheme Annual Monitoring Report 2012-13

June 2013